## Sprint Report
Sprint Name | Issue Type | Key | parent | Sub_Task | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date | Logged Time | Time in Hours
EFR 16 | Task | BLCV4PLUS-1537 |  |  | Feedback form issue fixed in course details API | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-01 05:38 | 2021-10-04 10:04 |  | 6h | 6h
EFR 16 | Task | BLCV4PLUS-1535 |  |  | Demo Application UAT comments | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-01 04:38 | 2021-10-18 03:43 |  | 1w 1d 5h 30m | 69h 30m
EFR 16 | Task | BLCV4PLUS-1534 |  |  | BLC - 5.0 push to hub Mastering India instance | Praveen Vishwakarma | Vignesh Munisamy | Medium | Topic Definition |  | 2021-09-29 12:41 | 2021-10-27 04:18 |  | 1d 1h 30m | 9h 30m
EFR 16 | Sub_Task |  | BLCV4PLUS-1534 | BLCV4PLUS-1536 | hub Masterindia - Preprod Setup the applciation | Praveen Vishwakarma | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-01 06:38 | 2021-10-04 12:03 |  | 1h 30m | 1h 30m
EFR 16 | Sub_Task |  | BLCV4PLUS-1534 | BLCV4PLUS-1563 | BLC- 5.0 push to MasteringIndia instance Analytics Module update & Verification | Esakkidoss P | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-18 08:07 | 2021-10-18 08:08
EFR 16 | Sub_Task |  | BLCV4PLUS-1534 | BLCV4PLUS-1564 | BLC- 5.0 push to SDGPlus instance - EFR Sprint 1 -12 changes update | Praveen Vishwakarma | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-18 08:07 | 2021-10-18 08:08
EFR 16 | Sub_Task |  | BLCV4PLUS-1534 | BLCV4PLUS-1565 | BLC- 5.0 push to Mastering India instance - Content Migration | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-18 08:08 | 2021-10-18 08:08
EFR 16 | Sub_Task |  | BLCV4PLUS-1534 | BLCV4PLUS-1566 | Go Live | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-18 08:08 | 2021-10-18 08:09
EFR 16 | Story | BLCV4PLUS-1533 |  |  | Pro Partner Implementation | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-09-29 12:41 | 2021-10-04 10:04 |  | 1d 3h | 11h
EFR 16 | Task | BLCV4PLUS-1532 |  |  | Sprint Plan + Team Verification | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-29 12:40 | 2021-10-04 10:04 |  | 1d | 8h
EFR 16 | Task | BLCV4PLUS-1531 |  |  | Sprint Plan + Team Verification | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-29 12:40 | 2021-10-04 10:02 |  | 1d 2h | 10h
EFR 17 | Task | BLCV4PLUS-1554 |  |  | Sprint Plan + Team Verification | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 03:47 | 2021-10-19 04:20 |  | 2d 2h | 18h
EFR 17 | Sub_Task |  | BLCV4PLUS-1554 | BLCV4PLUS-1567 | Mobile Feature Discussion | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-18 12:57 | 2021-10-19 06:17 |  | 3h | 3h
EFR 17 | Sub_Task |  | BLCV4PLUS-1554 | BLCV4PLUS-1568 | GIT Issues | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-18 12:58 | 2021-10-19 06:17 |  | 3h | 3h
EFR 17 | Task | BLCV4PLUS-1542 |  |  | Team Course / Exp / Eve Listing | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 03:44 | 2021-10-19 04:19
EFR 17 | Sub_Task |  | BLCV4PLUS-1542 | BLCV4PLUS-1549 | Teams LazyLoading Need to be Implement | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18 |  | 6h | 6h
EFR 17 | Sub_Task |  | BLCV4PLUS-1542 | BLCV4PLUS-1550 | Team Course / Exp / Eve With Filter | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:46 | 2021-10-19 06:19 |  | 1d 4h | 12h
EFR 17 | Sub_Task |  | BLCV4PLUS-1542 | BLCV4PLUS-1551 | Pro Partner - Course Details Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:46 | 2021-10-19 06:19 |  | 4h | 4h
EFR 17 | Sub_Task |  | BLCV4PLUS-1542 | BLCV4PLUS-1552 | Pro Partner - Exp Details Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:46 | 2021-10-19 06:19 |  | 4h | 4h
EFR 17 | Sub_Task |  | BLCV4PLUS-1542 | BLCV4PLUS-1553 | Pro Partner - Events Details Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:46 | 2021-10-19 06:19 |  | 3h | 3h
EFR 17 | Task | BLCV4PLUS-1541 |  |  | Pro Partner Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 03:44 | 2021-10-19 04:19
EFR 17 | Sub_Task |  | BLCV4PLUS-1541 | BLCV4PLUS-1543 | Search Need to be Implement on Teams | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18 |  | 4h | 4h
EFR 17 | Sub_Task |  | BLCV4PLUS-1541 | BLCV4PLUS-1544 | Home,Our Course,About Us and Search Bar icon Menu links need to enabled | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18 |  | 5h | 5h
EFR 17 | Sub_Task |  | BLCV4PLUS-1541 | BLCV4PLUS-1545 | Show Course/Experience/events Count on Team Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18 |  | 1d 3h | 11h
EFR 17 | Sub_Task |  | BLCV4PLUS-1541 | BLCV4PLUS-1546 | About Us need to implement for Team | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18
EFR 17 | Sub_Task |  | BLCV4PLUS-1541 | BLCV4PLUS-1547 | Static Content section needs to enabled | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18 |  | 1d | 8h
EFR 17 | Sub_Task |  | BLCV4PLUS-1541 | BLCV4PLUS-1548 | View all course where it will redirect on Pro partner Details page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:45 | 2021-10-19 06:18 |  | 2h | 2h
EFR 17 | Task | BLCV4PLUS-1540 |  |  | Menu Re-ordering For All the roles | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-13 03:43 | 2021-10-27 04:19
EFR 17 | Task | BLCV4PLUS-1530 |  |  | HUB Language Translation for v5.0 |  | Vignesh Munisamy | Medium | Topic Definition |  | 2021-09-09 04:10 | 2021-10-27 04:29
EFR 17 | Story | BLCV4PLUS-1526 |  |  | Pro Admin Landing Implementation | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 04:10 | 2021-10-19 04:23
EFR 17 | Sub_Task |  | BLCV4PLUS-1526 | BLCV4PLUS-1527 | Specification Writing / Document Creation | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:10 | 2021-10-19 12:02 |  | 4h | 4h
EFR 17 | Sub_Task |  | BLCV4PLUS-1526 | BLCV4PLUS-1528 | Pro Partner - Admin Section | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:10 | 2021-10-19 06:21 |  | 3d 3h | 27h
EFR 17 | Sub_Task |  | BLCV4PLUS-1526 | BLCV4PLUS-1528 | Home Page | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:10 | 2021-10-04 12:02 |  | 2h | 2h
EFR 17 | Task | BLCV4PLUS-1519 |  |  | BLC - 5.0 push to Demo Hub & Hub SLX Learning instance | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 04:08 | 2021-10-27 04:30 |  | 2w 4d
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1520 | BLC- 5.0 push to Demo Hub Learning instance | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:09 | 2021-10-04 12:02 |  | 4d 7h | 39h
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1521 | BLC- 5.0 push to Demo Hub Learning instance | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:09 | 2021-10-04 12:02
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1522 | BLC- 5.0 push to Demo Hub Learning instance |  | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:09 | 2021-10-04 12:02
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1523 | BLC- 5.0 push to SLX instance | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:10 | 2021-10-27 06:29 |  | 1d 6h | 14h
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1524 | BLC- 5.0 push to SLX instance | Esakkidoss P | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:10 | 2021-10-27 06:29
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1525 | BLC- 5.0 push to SLX instance | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-09-09 06:09 | 2021-10-04 12:02 |  | 3d 4h | 28h
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1538 | hub SLX Learning - Preprod Setup the application | Sunil M | Vignesh Munisamy | Medium | Closed | Done | 2021-10-01 08:14 | 2021-10-04 12:02 |  | 1h | 1h
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1539 | Go Live for Hub SLX Learning |  | Vignesh Munisamy | Medium | Closed | Done | 2021-10-13 05:43 | 2021-10-27 06:29 |  | 4h | 4h
EFR 17 | Sub_Task |  | BLCV4PLUS-1519 | BLCV4PLUS-1569 | Application - Performance Management | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-19 07:03 | 2021-10-27 06:29 |  | 1d | 8h
POS 1 | Task | BLCV4PLUS-1585 |  |  | Analyse Page List | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-27 07:41 | 2021-11-08 05:38 |  | 2h
POS 1 | Task | BLCV4PLUS-1576 |  |  | Reduce Page Request | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-22 04:29 | 2021-11-08 05:35
POS 1 | Task | BLCV4PLUS-1570 |  |  | Performance optimization - BLC | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 04:24 | 2021-11-08 05:35 |  | 1d 4h | 12h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1571 | Server Configuration | Sunil M | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:25 | 2021-11-08 06:37
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1572 | Redis / Amazon Elasticcache & AWS Drupal Deployment Document & Mysql Server Upgrade | Sunil M | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:25 | 2021-11-08 06:36 |  | 1h | 1h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1573 | Aggregate and compression | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:26 | 2021-11-08 06:50 |  | 3h | 3h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1574 | Minification | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:28 | 2021-11-08 06:35 |  | 2h | 2h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1575 | Functional Block | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:28 | 2021-11-08 06:35
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1577 | Serve images in next-gen formats | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:30 | 2021-11-08 06:50 |  | 1d 3h 30m | 11h 30m
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1578 | Properly Size Image | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:30 | 2021-11-08 06:50 |  | 1d 30m | 8h 30m
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1579 | Reduce unused JavaScript / CSS | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:30 | 2021-11-08 06:50 |  | 3h | 3h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1580 | Reduce initial server response time | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:31 | 2021-11-08 06:35 |  | 2h | 2h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1581 | Drupal Optimization Steps | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:31 | 2021-11-08 06:35 |  | 1d | 8h
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1582 | MYSQL Slow Queries | Sunil M | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:35 | 2021-11-08 06:36 |  | 30m | 30m
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1583 | Enable HTTP/2 in Apache | Sunil M | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:36 | 2021-11-08 06:36 |  | 30m | 30m
POS 1 | Sub_Task |  | BLCV4PLUS-1570 | BLCV4PLUS-1584 | Local Cache | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-22 06:36 | 2021-11-08 06:36
POS 2 | Task | BLCV4PLUS-1600 |  |  | UAT - Comment - Hub SLX Learning | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 04:46 | 2021-11-08 05:52
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1601 | We need a sign up button along with Sign-In on Header | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 04:47 | 2021-11-08 06:52 |  | 1h | 1h
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1602 | The SDG renewable energy banner has no link ie. Home Banner Slider having no link | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:47 | 2021-11-08 06:52
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1603 | What is the rationale for learning objectives being listed before course description? Course description need to place before the Leanring Objective on course details and Lp details page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:47 | 2021-11-08 06:52 |  | 1h | 1h
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1604 | No tracker selectable, hence can’t submit a ticket | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:47 | 2021-11-08 06:52 |  | 1h | 1h
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1605 | Google Icon are overlapping? On user register & Login Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:48 | 2021-11-08 06:52 |  | 2h | 2h
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1606 | Instructor Name Spacing on course details Page | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:48 | 2021-11-08 06:52 |  | 1h | 1h
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1607 | Profile Edit Page Design Issue | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:49 | 2021-11-08 06:52 |  | 6h | 6h
POS 2 | Sub_Task |  | BLCV4PLUS-1600 | BLCV4PLUS-1608 | Course Details design issues | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-11-05 05:49 | 2021-11-08 06:52 |  | 5h 30m | 5h30m
POS 2 | Task | BLCV4PLUS-1597 |  |  | Performance optimization | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-28 04:36 | 2021-11-08 05:39 |  | 3d 3h
POS 2 | Task | BLCV4PLUS-1590 |  |  | Go Live - Version 5.1.0 | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 04:29 | 2021-10-28 04:31
POS 2 | Sub_Task |  | BLCV4PLUS-1590 | BLCV4PLUS-1591 | Demo Hub - Go Live - Version 5.1.0 | Esakkidoss P | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 06:29 | 2021-10-28 06:32
POS 2 | Sub_Task |  | BLCV4PLUS-1590 | BLCV4PLUS-1592 | Demo Hub - Go Live - Version 5.1.0 | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 06:29 | 2021-10-28 06:32
POS 2 | Sub_Task |  | BLCV4PLUS-1590 | BLCV4PLUS-1593 | Demo Hub - Go Live - Version 5.1.0 | Praveen Vishwakarma | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 06:30 | 2021-10-28 06:32
POS 2 | Sub_Task |  | BLCV4PLUS-1590 | BLCV4PLUS-1594 | Hub SLX - Go Live - Version 5.1.0 | Esakkidoss P | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 06:30 | 2021-10-28 06:32
POS 2 | Sub_Task |  | BLCV4PLUS-1590 | BLCV4PLUS-1595 | Hub SLX - Go Live - Version 5.1.0 | Vignesh Munisamy | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 06:30 | 2021-10-28 06:32
POS 2 | Sub_Task |  | BLCV4PLUS-1590 | BLCV4PLUS-1596 | Hub SLX - Go Live - Version 5.1.0 | Praveen Vishwakarma | Vignesh Munisamy | Medium | Topic Definition |  | 2021-10-28 06:30 | 2021-10-28 06:32
POS 2 | Task | BLCV4PLUS-1589 |  |  | BLC - List of the Forms' with Filed List | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-28 04:27 | 2021-11-08 05:39 |  | 1d 2h | 10h
POS 2 | Task | BLCV4PLUS-1588 |  |  | Image Optimization - BLC | Praveen Vishwakarma | Vignesh Munisamy | Medium | Closed | Done | 2021-10-28 04:26 | 2021-11-08 05:39 |  | 5h | 5h
POS 2 | Task | BLCV4PLUS-1587 |  |  | BLC - Installed Module List with details | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-28 04:20 | 2021-11-08 05:39 |  | 3h | 3h
POS 2 | Task | BLCV4PLUS-1586 |  |  | BLC Architecture - Update | Vignesh Munisamy | Vignesh Munisamy | Medium | Closed | Done | 2021-10-28 04:19 | 2021-11-08 05:39 |  | 7h | 7h

## Reference
Sprints/Task Completed in Sep 2021
EFR Sprint 17
BLCV4PLUS-1543 | Search Need to be implement for Teams
BLCV4PLUS-1544 | Home,Our Course,About Us and Search Bar icon Menu links need to enabled
BLCV4PLUS-1545 | Show Course/Experience/events Count on Team Page
BLCV4PLUS-1546 | About Us need to implement for Team
BLCV4PLUS-1547 | Static Content section needs to enabled
BLCV4PLUS-1548 | View all course where it will redirect on Pro partner Details page
BLCV4PLUS-1549 | Teams Lazy Loading need to be implement
BLCV4PLUS-1550 | Team Course with Filter
BLCV4PLUS-1550 | Team Experience with Filter
BLCV4PLUS-1550 | Team Events with Filter
BLCV4PLUS-1551 | Pro Partner - Course Details page
BLCV4PLUS-1552 | Pro Partner - Exp Details page
BLCV4PLUS-1553 | Pro Partner - Events Details page
| Hub SLX Migration Script | not in EFR 17
EFR Sprint 16
| Demo hub Application QA verification + Bug fixing | not in EFR 16
| EFR Sprint 1-12 Release on PreProdhub SLX Learning instance [Content migration is pending ] | not in EFR 16
| Initiated EFR Sprint Release on PreProdhub Mastering India instance | not in EFR 16
| Pro partner - Home Page, Pro partner page with lazy load, Search | not in EFR 16
| Pro partner & Team Landing page | not in EFR 16
POS Sprint 1
BLCV4PLUS-1571 | Apache - Keep Alive
BLCV4PLUS-1571 | MPM Module
BLCV4PLUS-1571 | gzip Module enabled
BLCV4PLUS-1571 | Memcache Module
BLCV4PLUS-1571 | PHP opcode caching
BLCV4PLUS-1572 | Redis / Amazon Elasticcache
BLCV4PLUS-1572 | AWS Drupal Deployment Document
BLCV4PLUS-1572 | Mysql Server Upgrade
BLCV4PLUS-1573 | Aggregate and compression on Master
| Minification on Master | Not In POS1
| Enable Opcache & Redis in the BLC application | Not In POS1
| Performance Optimization on the BLC - explore & popular choice block | Not In POS1
POS Sprint 2
| Performance optimization for Course | Not In POS2
| Below Pages | Not In POS2
| Sign up | Not In POS2
| Log in | Not In POS2
| Become a Partner | Not In POS2
| Partner Plan | Not In POS2
| Terms & Condition | Not In POS2
| About Us | Not In POS2
| Install Redis module & Configure on | Not In POS2
| the Event | Not In POS2
| Redis Module | Not In POS2
BLCV4PLUS-1597 | Minify HTML
BLCV4PLUS-1597 | Aggregation CSS/JS
| DB Maintenance | Not In POS2
| BLC - Architecture Diagram | Not In POS2
BLCV4PLUS-1598 | BLC - Workflow List
BLCV4PLUS-1588 | BLC - Image Optimization